## Site Pages
Page | Purpose | Status | Anchor scripture
index.html | Home + featured scriptures + welcome | BUILT | Psalm 122:6
mission.html | Mission statement (Isaiah 49:22 anchor) | BUILT | Isaiah 49:22
story.html | Clark's 47-year testimony | BUILT | —
music.html | Hebrew worship + Shabbat blessings + Yeshua haMashiach | BUILT | Psalm 30:4
jerusalem.html | Vision · Eastern Gate · 8 reasons · prophecy | BUILT | Zechariah 14:4
resources.html | 64 Aliyah Scriptures · 8 Things · Esther Fast · Tallit | BUILT | Acts 17:11

## Brand Identity
Element | Value | Use
Israeli Blue | #0038B8 | h2 · primary links
Forest Green | #2D6A4F | h3 · scripture anchors
Rust Brown | #8B5E3C | h4 · Jerusalem stone tone
Red Emphasis | #B22222 | Prophecy · fulfilled-scripture callouts
Deep Blue | #203A56 | Header · footer
Cream | #F6F1E6 | Warm background
Serif font | EB Garamond | Body text
Sans font | Source Sans 3 | UI · headings

## Eight Things
# | Theme | Scripture
1 | Comfort God's People | Isaiah 40:1
2 | Praying for and Watching Over Jerusalem | Psalm 122:6 · Isaiah 62:6-7
3 | Carry — Support Aliyah | Isaiah 49:22
4 | Show Mercy | Romans 11:30-31
5 | Contribute Materially | Romans 15:27 · Isaiah 60:5-6
6 | Provoke to Jealousy | Romans 11:11
7 | Proclaim | Isaiah 52:7
8 | Bless and Do NOT Curse | Genesis 12:1-3

## Pre-Launch Gaps
# | Gap | Severity | Owner | Unlock
1 | Zechariah 12:6-10 verification (was typo'd as Zech 17:6-10) | CRITICAL | Clark | 5 min
2 | Hosting decision (IONOS · Hostinger · Vercel) | CRITICAL | Clark + Sandi | 30 min call
3 | Domain DNS configuration | CRITICAL | Clark | 10 min once host chosen
4 | First production deploy | CRITICAL | Sandi | 1 sitting after #2 + #3
5 | Cross-browser QA (6 browsers) | HIGH | Sandi | 2-3 sittings
6 | Mobile responsive QA on real devices | HIGH | Sandi | 1 sitting
7 | Lighthouse audit (target 90+) | HIGH | Sandi | 1 sitting + fixes