## Market Sizing
Segment | 2024-2025 Valuation | 2030-2036 Projection | CAGR
Space Robotics & Autonomous Systems | USD 5.4-6.6 B | USD 12.4-17.9 B | 8.6-9.5%
In-Orbit Satellite Servicing | USD 1.27-4.67 B | USD 9.0-12.6 B | 10.4-10.8%
Space Debris Monitoring & Removal | USD 1.05-1.45 B | USD 2.05-4.12 B | 7.8-18.7%

## Peer Public Markets
Company | Public-market event | Their model | What they leave on the table
Astroscale | 2024 Tokyo IPO | Capture + deorbit ADR-as-service | Captured material destroyed in re-entry — value lost
ClearSpace | €100M institutional · ESA prime | Single-target Pac-Man grappler | One-shot architecture · no persistent presence · no recovery loop
Redwire | 2021 SPAC merger (NYSE: RDW) | Robotics-as-a-Service for satellite operators | Servicing focus · no debris-recovery posture
Icarus (us) | Pre-seed validation | Distributed Dragonfly fleet + PTOT + OPS recovery loop | (filling the gap)

## 5-Stage Roadmap
Stage | Window | Milestone
1: Validation | now → 12 mo | NSS Rothblatt · investor materials · Phase 1 funding
2: Prototype | mo 12-30 | DF-1 ground prototype · propulsion test articles
3: Demo Mission | mo 30-48 | Single-drone capture demo · partner-funded
4: Operational | yr 4-6 | Small flotilla · paying contracts · first material recovery
5: Industrial | yr 6+ | OPS infrastructure · recovery economy break-even

## Pre-ISDC Gaps
# | Gap | Severity | Owner | Unlock
1 | Investor packet contact block | CRITICAL | Sandi | 5 min
2 | Designer hand-off for typeset PDF | CRITICAL | Sandi · designer | Brief + 7 days
3 | Packet hosting URL decision | CRITICAL | Sandi + Shawn | 30 min
4 | Real QR for flyer | CRITICAL | Sandi | 5 min after URL stable
5 | NASA Langley advisor naming policy | CRITICAL | Sandi + Troy + advisor | Coordination
6 | ESA 2024 number verified | HIGH | Sandi | 30 min
7 | Conference table location confirmed | HIGH | Sandi | 1 email
8 | iPad demo loop prepared | HIGH | Sandi | 1 sitting
9 | Travel + lodging booked | HIGH | Sandi | 1 sitting