## Revenue Projection
Quarter | Tier 1 (book) | Tier 2 (course) | Tier 3 (cohort) | Total
Q1 (post-launch) | 2000 | 9850 | 2844 | 14694
Q2 | 1200 | 7880 | 7110 | 16190
Q3 | 1000 | 6895 | 10665 | 18560
Q4 | 1600 | 9850 | 14220 | 25670
Y1 TOTAL | 5800 | 34475 | 34839 | 75114

## Tier Ladder
Tier | Name | Price | What unlocks | Revenue role
1 | Book Reader | ~$14.99 paperback / $4.99 Kindle | Book + intro module + email sequence | Front door · top of funnel
2 | Course Member | $197 one-time OR $29/mo | Full Four Realms course · journal prompts · scripture library | Core revenue
3 | Cohort Member | $79/mo (rolling) | Tier 2 + monthly group call + accountability partner matching | Premium · highest LTV

## 90-Day Schedule
Phase | Days | Major milestones | Owner
1: Book to KDP | 1-30 | Editorial · cover · KDP upload · proof copy · live | Sandi
2: Platform MVP | 31-60 | MySQL · auth · Stripe · Module 1 · soft launch | Shawn + Sandi
3: First cohort | 61-90 | Cohort enrollment · first call · iteration | Sandi

## Gap Priority
# | Gap | Severity | Owner | Effort
1 | Book editorial pass not started | CRITICAL | Sandi | 5 sittings
2 | Cover designer not engaged | CRITICAL | Sandi → designer | Brief + 2wk turnaround
3 | Three Truths consistency audit | CRITICAL | Sandi | 2 sittings
4 | KDP description (4000 char) | CRITICAL | Sandi | 1 sitting
5 | Author photo dated | CRITICAL | Sandi | 1 photo session
6 | MySQL schema not deployed | HIGH | Shawn or Sandi | 1 sitting
7 | Stripe live keys not configured | HIGH | Sandi | 30 min
8 | bootstrap.php / auth.php for kingdom-wife/ | HIGH | Shawn | 2 sittings
9 | Course Module 1 (Inner Life) content | HIGH | Sandi | 3 sittings
10 | Email sequence Day 0/3/7/14/30 | HIGH | Sandi | 1 sitting